## Contract
| Totale workload | 100% | Dit moet 100% zijn.
Number | Feature (Groep) | Naam | Workload | Geschatte tijdsbesteding | Done? | Lid | Dit moet tussen de 60 en de 75 liggen
0 | Brainstorm | Emil Lambert | 2.8% | 7 | V | Anas Stitou | 64
0 | Brainstorm | Anas Stitou | 2.8% | 7 | V | Emil Lambert | 61
0 | Brainstorm | Tibo Verreycken | 2.8% | 7 | V | Tibo Verreycken | 64
0 | Brainstorm | Kars Christian van Velzen | 2.8% | 7 | V | Kars Christian van Velzen | 61
[6 empty] | Totaal | 250
1 | Unificatie | Anas Stitou | 1.2% | 3 | X
1.1 | Class Design | Anas Stitou | 1.2% | 3 | X
2 | Parser | Tibo Verreycken | 3.6% | 9 | X
2.1 | Split | Tibo Verreycken | 0.8% | 2 | X
2.2 | Add Data in Classes | Tibo Verreycken | 0.8% | 2 | X
X
3 | Regex Constructor | Emil Lambert |  |  | X
3.1 | toRegex() | Emil Lambert | 2.4% | 6 | X
3.2 | toRegexChannel() | Emil Lambert | 1.2% | 3 | X
3.3 | toRegexVelocity | Emil Lambert | 1.2% | 3 | X
3.4 | toRegexLettersNote | Anas Stitou | 1.6% | 4 | X
3.5 | toRegexToonHoogte() | Anas Stitou | 1.2% | 3 | X
3.6 | toRegexInstrument() | Anas Stitou | 0.8% | 2 | X
4 | Similarity | Kars Christian van Velzen |  |  | X
4.1 | Full Similarity | Kars Christian van Velzen | 1.2% | 3 | X
4.2 | Similarity % | Kars Christian van Velzen | 3.6% | 9 | X
4.3 | Check Reverse Similarity % | Kars Christian van Velzen | 0.8% | 2
4.4 | Check Complement Similarity % | Tibo Verreycken | 0.8% | 2
4.H1 | Complement DFA | Tibo Verreycken | 1.2% | 3 | X
4.H2 | Reverse DFA | Tibo Verreycken | 2.4% | 6 | X
X
5 | Categoriseren | Anas Stitou | 3.6% | 9 | X
5.1 | 2 Songs in 1 Groep | Anas Stitou | 2.4% | 6 | X
5.2 | Check if Song in Groep | Anas Stitou | 2.4% | 6
6 | Output Results | Kars Christian van Velzen |  |  | X
6.1 | Output Console | Kars Christian van Velzen | 2.4% | 6 | X
6.2 | Output File | Kars Christian van Velzen | 1.2% | 3 | X
6.3 | Output Song (.mid) | Tibo Verreycken | 3.6% | 9
7 | Random Song Generator | Anas Stitou | 2.4% | 6 | X
7.1 | Integratie State Elimination | Emil Lambert | 1.2% | 3 | X
7.2 | Make Random Song from 2 Songs | Anas Stitou | 2.4% | 6
X
8 | Note Rounder | Tibo Verreycken | 1.2% | 3 | X
9 | Documentatie | Kars Christian van Velzen | 2.4% | 6 | X
9.1 | About .mid | Kars Christian van Velzen | 0.8% | 2 | X
9.2 | Administration | Kars Christian van Velzen | 2.4% | 6 | X
9.3 | Visualisation | Kars Christian van Velzen | 0.8% | 2 | X
9.4 | Portfolio | Kars Christian van Velzen | 2.4% | 6
10 | GUI | Tibo Verreycken | 4.8% | 12 | X
X
11 | Testing | Emil Lambert | 3.6% | 9 | X
11 | Testing | Anas Stitou | 3.6% | 9
11 | Testing | Tibo Verreycken | 3.6% | 9
11 | Testing | Kars Christian van Velzen | 3.6% | 9
X
12 | Note Counter | Emil Lambert | 3.6% | 9 | X
12.1 | GJDFA / General One-Way-Jumping FA | Emil Lambert | 4.8% | 12 | X
12.1 | Converter (JDFA to RE) | Emil Lambert | 3.6% | 9 | X